## Test report
TEST REPORT
Project Name | Online learning system |  | Creator |  |  | ThaiLH
Project Code | OLS |  | Reviewer/Approver
Document Code | FOMS_Integration Test.xlsx |  | Issue Date |  |  | 2023-03-16
Notes
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Home page | 13 | 0 | 0 | 0 | 13
2 | UserLogin | 13 | 0 | 0 | 0 | 13
3 | UserRegister | 9 | 0 | 0 | 0 | 9
4 | ResetPassword | 4 | 0 | 0 | 0 | 4
5 | ChangePassword | 6 | 0 | 0 | 0 | 6
6 | ManageCourse | 6 | 0 | 0 | 0 | 6
7 | ManageLesson | 6 | 0 | 0 | 0 | 6
8 | ManageFlashCard | 6 | 0 | 0 | 0 | 6
9 | ManageBlog | 4 | 0 | 0 | 0 | 4
10 | Profile | 7 | 0 | 0 | 0 | 7
| Sub total | 74 | 0 | 0 | 0 | 74
| Test coverage | 100%
| Test successful coverage | 100%

## Home page
Back to TestReport | To Buglist | Pass: 13 | Untested: 0
Module Code | Home page | Fail: 0 | N/A: 0
Tester | Le Hoang Thai | Percent Complete: 100% | Number of cases: 13
ID | Test Case Description | Test Case Procedure | Expected Output | Result Test | Test date | Note
[Home page-1] | Verify Foreign Language in categories of course | 1. Click "Foreign Language" in categories of courses | 1. Page will link to Foreign Languge course page | Pass | 2011-10-09 | Basic flow
[Home page-2] | Verify Mathematic in categories of course | 1. Click "Mathematic" in categories of courses | 1. Page will link to Mathematic course page | Pass | 2011-10-09 | Basic flow
[Home page-3] | Verify Engineering in categories of course | 1. Click "Engineering" in categories of courses | 1. Page will link to Engineering course page | Pass | 2011-10-09 | Basic flow
[Home page-4] | Verify Business in categories of course | 1. Click "Business" in categories of courses | 1. Page will link to Business course page | Pass | 2011-10-09 | Basic flow
[Home page-5] | Verify Others in categories of course | 1. Click "Others" in categories of courses | 1. Page will link to Others course page | Pass | 2011-10-09 | Basic flow
[Home page-6] | Verify Profile, Manage Account and Log Out below avatar with admin account | 1. Hover to avatar and drop Profile, Manage Account and Log Out | 1. Avatar drop-down Profile, Manage Account and Log Out | Pass | 2011-10-09 | Basic flow
[Home page-7] | Verify Profile, Manage Course, Manage Lesson and Log Out below avatar with expert account | 1. Hover to avatar and dropProfile, Manage Course, Manage Lesson and Log Out | 1. Avatar drop-down Profile, Manage Course, Manage Lesson and Log Out | Pass | 2011-10-09 | Basic flow
[Home page-8] | Verify Profile, Manage Blog and Log Out below avatar with seller account | 1. Hover to avatar and drop Profile, Manage Blog and Log Out | 1. Avatar drop-down Profile, Manage Blog and Log Out | Pass | 2011-10-09 | Basic flow
[Home page-9] | Verify Profile,Log Out below avatar with admin account | 1. Hover to avatar and drop Profile and Log Out | 1. Avatar drop-down Profile and Log Out | Pass | 2011-10-09 | Basic flow
[Home page-10] | Verify My Course in menu-bar with student account | 1. Login with student account and My Course appear in menu-bar 2. Click on My Course | 1. Home page next to My Course page include all course enrolled | Pass | 2011-10-09 | Basic flow
[Home page-11] | Verify Enroll Course in body home page with student account | 1. Scroll to the courses in near footer of home page 2. Click to the Enroll course | 1. Course add to My Course 2. Student can view lesson and flashcard in course | Pass | 2011-10-09 | Basic flow
[Home page-12] | Verify log out below avatar | 1. Click to log out in drop-down menu below avatar 2. Click to Log out | 1. Account log out and page next to the log in page | Pass | 2011-10-09
[Home page-13] | Verify blog in menu-bar | 1. Click to Blog | 1. Page next to Blog page | Pass | 2011-10-09 | Alternative flow

## Login
Back to TestReport | To Buglist | Pass: 13 | Untested: 0
Module Code | UserLogin | Fail: 0 | N/A: 0
Tester | Vu Van Tuan | Percent Complete: 100% | Number of cases: 13
ID | Test Case Description | Test Case Procedure | Expected Output | Result Test | Test date
[UserLogin-] | Show pop-up'Login" | 1.0pen Online learning website in the Internet 2.Click button 'Login' in the Home page 3:Click button 'Login' | 1. The Login is displayed 2. The "Login" view form is displayed with the folowing informations : -User name -Password -Button "Login" | Pass | 14/03/2023
[UserLogin-2] | Verify login successfully | Tap to type registered email of "vietanhlm69@gmail.com" & password of "12345678", then submit to login | 2. Online Learning dashboard appears, including: 2a. Categories of courses and can enroll courses 2b. Avatar to logout, edit profile, change password | Pass | 14/03/2024
[UserLogin-2] | Check validate "Login with account Admin | 1. Enter correct value usergmail "admin@gmail.com" 2. Enter correct value pass "123" 3. Click button"Login" | Display Admin page with Admin account | Pass | 14/03/2025
[UserLogin-3] | Check validate "Login with account Expert | 1. Enter correct value usergmail "expert1@gmail.com" 2. Enter correct value pass "123" 3. Click button"Login" | Display Expert page with Expert account | Pass | 14/03/2026
[UserLogin-4] | Check validate "Login with account Seller | 1. Enter correct value usergmail "seller1@gmail.com" 2. Enter correct value pass "123" 3. Click button"Login" | Display Seller page with Seller account | Pass | 14/03/2027
[UserLogin-5] | Check validate "Login with account Student | 1. Enter correct value usergmail "vietanhlm69@gmail.com" 2. Enter correct value pass "123" 3. Click button"Login" | Display Student page with Student account | Pass | 14/03/2028
[UserLogin-7] | Verify password is in pair with email address | 1. Tap to type email address like "vietanhlm69@gmail.com" 2. Tap on password and type "aaabbbccc", then submit to login | 1. Alert appears to inform, like "Wrong email or password!!!" | Pass | 14/03/2029
[UserLogin-8] | Verify Forgot password button work | 1. Tap on "Forgot Password" | 1. Go to "Forgot Password" page | Pass | 14/03/2030
[UserLogin-9] | Verify "Don't have an account, create new" link work | 1. Tap on "Don't have an account, create new" | 1. Go to "Register page | Pass | 14/03/2031
[UserLogin-10] | Verify logout | Tap on Log Out | 1. Go back to the login page | Pass | 14/03/2032
[UserLogin-11] | Verify login session expired in 30 minutes | 1. Login successfully and wait for over 30 minutes | 1. Login session will end. User can not submit or go to next page in OL. User will be gone back to login page of OL | Pass | 14/03/2033
[UserLogin-12] | Verify logout | Tap on Log Out | 1. Go back to the login page | Pass | 14/03/2034
[UserLogin-13] | Verify login session NOT expired in less than 30 minutes | 1. Login successfully and wait in less than 30 minutes | 1. Login session still remains | Pass | 14/03/2035

## Register
Back to TestReport | To Buglist | Pass: 9 | Untested: 0
Module Code | UserRegister | Fail: 0 | N/A: 0
Tester | Le Tuan Duc | Percent Complete: 100% | Number of cases: 9
ID | Test Case Description | Test Case Procedure | Expected Output | Result Test | Test date | Note
[UserRegister] | Show pop-up"Register" | 1.0pen Online learning website in the Internet 2.Click button 'Login' in the Home page 3:Click button 'Create new' | 1. The Register is displayed 2. The "Register" view form is displayed with the folowing informations : -Name - Email - Password - Re-enter Password -Gender - Date of birth - Phone Number -Button "Back" -Button"Register" | Pass | 14/03/2023 | Basic flow
[UserRegister-2] | Verify Create Account button work | 1. Fill Name, Email,password, re-enter password, gender,date of birth, phone. 2. Click button Register | 1. Go to homepage | Pass | 14/03/2023 | Basic flow
[UserRegister-3] | Verify gmail is not accepted to be lack of "@gmail.com" | Tap to type registered email of "duc123" then submit to login | 1. Alert appears to inform, like email is required” | Pass | 14/03/2023 | Alternative flow
[UserRegister-4] | Verify date of birth is not accepted to be blank | 1. Tap not to type a date of birth, then submit | 1. Alert appears to inform, like Date of birth is required” | Pass | 14/03/2023 | Alternative flow
[UserRegister-5] | Verify Name is not accepted to be blank | 1. Tap not to type a Name, then submit | 1. Alert appears to inform, like Name is required” | Pass | 14/03/2023 | Alternative flow
[UserRegister-6] | Verify password is not accepted to be blank | 1. Tap not to type a password, then submit | 1. Alert appears to inform, like Password is required” | Pass | 14/03/2023 | Alternative flow
[UserRegister-7] | Verify phone is not accepted to be blank | 1. Tap not to type a phone, then submit | 1. Alert appears to inform, like Phone is required” | Pass | 14/03/2023 | Alternative flow
[UserRegister-8] | Verify phone is not formatted correctly | 1. Tap not to type a phone like "22124124", then submit | 1. Alert appears to inform, like Phone is required” | Pass | 14/03/2023 | Alternative flow
[UserRegister-9] | Verify re-enter password need match with password | 1. Tap to type a password like "123", type a re-enter passsword lik "234" then submit | 1. Alert appears to inform, like "Password does not match, try again" | Pass | 14/03/2023 | Alternative flow

## ResetPassword
nnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnn | To Buglist |  | Pass: 4 | Untested: 0
Module Code | ResetPassword |  | Fail: 0 | N/A: 0
Tester | Nguyen Duc Huy |  | Percent Complete: 100% | Number of cases: 4
ID | Test Case Description | Pre -Condition | Test Case Procedure | Expected Output | Result Test | Test date | Note
[ResetPassword-1] | Verify do Forgot Password successfully | Access Online Learning, user is not logged in before | 1. Tap on Forgot Password 2. Input registered email, then submit 3. Check the email to get code 4. Input new password 5. Re-Input new password | 1.New password is encrypted in account table 2.Go back to Login page | Pass | 14/03/2023 | Basic flow
[ResetPassword-2] | Verify email address is not accepted to be blank | Access Online Learning, user is not logged in before | 1. Tap to submit without typing any email | 1. Alert appears to inform, like "Email is incorrect!!!" | Pass | 14/03/2023 | Alternative flow
[ResetPassword-3] | Verify email address exists | Access Online Learning, user is not logged in before | 1. Tap to type email address like "zyyyxxxyzzz", and submit | 1. Alert appears to inform, like "Email is incorrect!!!" | Pass | 14/03/2023 | Alternative flow
[ResetPassword-4] | Verify button login | Access Online Learning, user is not logged in before,press on "Forgot password ?" link | 1. Tap "login" button | 1. Back to login page | Pass | 14/03/2023 | Alternative flow

## ChangePassword
Back to TestReport | To Buglist |  | Pass: 6 | Untested: 0
Module Code | ChangePassword |  | Fail: 0 | N/A: 0
Tester | Nguyen Duc Huy |  | Percent Complete: 100% | Number of cases: 6
ID | Test Case Description | Pre -Condition | Test Case Procedure | Expected Output | Result on HTC Sensation | Test date | Note
[ChangePassword-1] | Verify do Change Password successfully | Access Online Learning and login successfull | 1. Tap on Profile 2. Tap on Change Password 3. Enter old password 4. Enter new password 4. Re-enter new password, then save | 1. New password encrypted in account table 2. Go back to home page | Pass | 2023-03-16 | Basic flow
[ChangePassword-2] | Verify Home link | Access Online Learning and login successfull | 1. Tap to Home link | 1. Go back to Home page | Pass | 2023-03-16 | Alternative flow
[ChangePassword-3] | Verify Category combobox | Access Online Learning and login successfull | 1. Tap to Category combobox 2. Select Category want to search | 1. Go back to Category page | Pass | 2023-03-16 | Alternative flow
[ChangePassword-4] | Verify My courses link | Access Online Learning and login successfull | 1. Tap to My course link | 1. Go back to My course page | Pass | 2023-03-16 | Alternative flow
[ChangePassword-5] | Verify Blogs link | Access Online Learning and login successfull | 1. Tap to Blogs link | 1. Go back to Blogs page | Pass | 2023-03-16 | Alternative flow
[ChangePassword-6] | Verify user combobox | Access Online Learning and login successfull | 1. Tap to User combobox 2. Select options want to do | 1. Go to options page | Pass | 2023-03-16 | Alternative flow

## Manage Course
Back to TestReport | To Buglist |  | Pass:6 | Untested: 0
Module Code | MangeCourse |  | Fail: 0 | N/A: 0
Tester | Le Tuan Duc |  | Percent Complete: 100% | Number of cases: 6
ID | Test Case Description | Test Case Procedure | Expected Output | Result test | Test date | Note
[MangeCourse-1] | Verify create a course | 1. Tap on Manage course 2. Tap to Create course 3. Tap to add course ID, courseID, course description, course name, image, category id then create | 1. A course is created and appeared on Course Dashboard | Pass | 14/03/2023 | Alternative flow
[MangeCourse-2] | Verify edit a course | 1. Tap on Manage course 2. Tap to "update" on course need update 3. Tap to edit course ID, course description, course name, image, category ID then update | 1. A course is updated and appeared on Course Dashboard | Pass | 14/03/2023 | Alternative flow
[MangeCourse-3] | Verify delete a course | 1. Tap on Manage course 2. Tap to "delete" on course need delete 3. Confirm you really want to delete this course | 1. A course is deleted and disappeared on Course Dashboard | Pass | 14/03/2023 | Alternative flow
[MangeCourse-4] | Verify view a course | 1. Tap on Manage course | 1. All course appeared on Course Dashboard | Pass | 14/03/2023 | Basic flow
[MangeCourse-5] | Verify confirm update screen | 1. Tap on Manage course 2. Tap to "update" on course | 1. Confirm update screen appeared | Pass | 14/03/2023 | Alternative flow
[MangeCourse-6] | Verify confirm delete screen | 1. Tap on Manage course 2. Tap to "delete" on course | 1. Confirm delete screen appeared | Pass | 14/03/2023 | Alternative flow

## Manage Lesson
Back to TestReport | To Buglist | Pass: 6 | Untested: 0
Module Code | ManageLesson | Fail: 0 | N/A: 0
Tester | Le Tuan Duc | Percent Complete: 100% | Number of cases: 6
ID | Test Case Description | Test Case Procedure | Expected Output | Result test | Test date | Note
[ManageLesson-1] | Verify create a lesson | 1. Tap on Manage lesson 2. Tap to Create lesson 3. Tap to add course ID, lessonID, lesson description, lesson name then create | 1. A lesson is created and appeared on Lesson Dashboard | Pass | 14/03/2023 | Alternative flow
[ManageLesson-2] | Verify edit a lesson | 1. Tap on Manage lesson 2. Tap to "update" on lesson need update 3. Tap to edit course ID, lesson description, lesson name then update | 1. A lesson is updated and appeared on Lesson Dashboard | Pass | 14/03/2023 | Alternative flow
[ManageLesson-3] | Verify delete a lesson | 1. Tap on Manage lesson 2. Tap to "delete" on lesson need delete 3. Confirm you really want to delete this lesson | 1. A lesson is deleted and disappeared on Lesson Dashboard | Pass | 14/03/2023 | Alternative flow
[ManageLesson-4] | Verify view a lesson | 1. Tap on Manage lesson | 1. All lesson appeared on Lesson Dashboard | Pass | 14/03/2023 | Basic flow
[ManageLesson-5] | Verify confirm update screen | 1. Tap on Manage lesson 2. Tap to "update" on lesson | 1. Confirm update screen appeared | Pass | 14/03/2023 | Alternative flow
[ManageLesson-6] | Verify confirm delete screen | 1. Tap on Manage lesson 2. Tap to "delete" on lesson | 1. Confirm delete screen appeared | Pass | 14/03/2023 | Alternative flow

## Manage Flashcard
Back to TestReport | To Buglist |  | Pass: 6 | Untested: 0
Module Code | ManageFlashCard |  | Fail: 0 | N/A: 0
Tester | Le Tuan Duc |  | Percent Complete: 100% | Number of cases: 6
ID | Test Case Description | Test Case Procedure | Expected Output | Result test | Test date | Note
[ManageFlashCard-1] | Verify create a flashcard | 1. Tap on Manage flashcard 2. Tap to add lesson ID, flashcardID, flashcard description, flashcard name then submit | 1. A flashcard is created and appeared on Flashcard Dashboard | Pass | 2023-03-14 | Alternative flow
[ManageFlashCard-2] | Verify edit a flashcard | 1. Tap on Manage flashcard 2. Tap to "update" on flashcard need update 3. Tap to edit course ID, flashcard description, flashcard name then update | 1. A flashcard is updated and appeared on Flashcard Dashboard | Pass | 2023-03-14 | Alternative flow
[ManageFlashCard-3] | Verify delete a flashcard | 1. Tap on Manage flashcard 2. Tap to "delete" on flashcard need delete 3. Confirm you really want to delete this flashcard | 1. A flashcard is deleted and disappeared on Flashcard Dashboard | Pass | 2023-03-14 | Alternative flow
[ManageFlashCard-4] | Verify view a flashcard | 1. Tap on Manage flashcard | 1. All flashcard appeared on Flashcard Dashboard | Pass | 2023-03-14 | Basic flow
[ManageFlashCard-5] | Verify confirm update screen | 1. Tap on Manage flashcard 2. Tap to "update" on flashcard | 1. Confirm update screen appeared | Pass | 2023-03-14 | Alternative flow
[ManageFlashCard-6] | Verify confirm delete screen | 1. Tap on Manage flashcard 2. Tap to "delete" on flashcard | 1. Confirm delete screen appeared | Pass | 2023-03-14 | Alternative flow

## Manage Blog
Back to TestReport | To Buglist | Pass: 4 | Untested: 0
Module Code | Blog | Fail: 0 | N/A: 0
Tester | Bui Viet Anh | Percent Complete: 100% | Number of cases: 4
ID | Test Case Description | Test Case Procedure | Expected Output | Result Test | Test date | Note
[Blog-1] | Verify create a blog | 1. Tap on Manage Blog 2. Tap to add Blog ID, Blog Title, Blog Detail, Blog image, Blog Date then submit | 1. A Blog is created and appeared on Blog Dashboard | Pass | 14/03/2023 | Alternative flow
[Blog-2] | Verify edit a blog | 1. Tap on Manage Blog 2. Tap to "update" on Blog need update 3. Tap to edit Blog ID, Blog Title, Blog Detail, Blog image, Blog Date then update | 1. A Blog is update and appeared on Blog Dashboard | Pass | 14/03/2023 | Alternative flow
[Blog-3] | Verify delete a blog | 1. Tap on Manage Blog 2. Tap to "delete" on blog need delete 3. Confirm you really want to delete this blog | 1. A blog is deleted and disappeared on Blog Dashboard | Pass | 14/03/2023 | Alternative flow
[Blog-4] | 1. All blog appeared on Blog Dashboard | 1. Tap on Manage Blog | 1. All Blog appeared on Blog Dashboard | Pass | 14/03/2023 | Basic flow

## View-Edit-Delete Profile
Back to TestReport | To Buglist | Pass: 7 | Untested: 0
Module Code | Profile | Fail: 0 | N/A: 0
Tester | Le Hoang Thai | Percent Complete: 100% | Number of cases: 7
ID | Test Case Description | Test Case Procedure | Expected Output | Result Test | Test date | Note
[Profile-1] | Verify view a profile | 1. Tap on a profile in avatar from dashboard | 1. A profile including following information appears: name, usergmail, born, gender, phone number | Pass | 14/03/2023 | Basic flow
[Profile-2] | Verify profile information | 1. Tap on a profile and view other content | 1. Info appears as followings: - Name - Usergmail(read only) - Born (mm/dd/yyyy) - Gender - Phone number - Button to save when change profile - Button to change password | Pass | 2023-03-14 | Alternative flow
[Profile-3] | Verify edit a profile | 1. Tap on a profile from Dashboard 2. Tap and type to edit information 3. Save | 1. Edit successfully, then go back to login | Pass | 2023-03-14 | Basic flow
[Profile-4] | Verify name is not blank or empty | 1. Tap not to type name | 1. Alert appears to inform name is not allowed to be empty | Pass | 2023-03-14 | Alternative flow
[Profile-5] | Verify phone number | 1. Tap to phone number to change information not like VN phone number | 1. Alert appears to inform phone number is must follow VN phone number | Pass | 2023-03-14
[Profile-6] | Verify date of birth | 1. Tap to change date of birth and choose later day | 1. Alert appears to inform dob is dob is invalid | Pass | 2023-03-14 | Alternative flow
[Profile-7] | Verify change password button | 1. Tap to change password button | 1. Page will next to change password page | Pass | 2023-03-14 | Alternative flow