## Sheet1
Feature | Function Name | Role | Function Description |  | Execution |  | In Charge | Document Link | Note
|  |  | Original Requirement | After Changing | Plan (days) | Actual (days)
Common Feature | User login | Admin, Seller, Expert, Student, Customer | These role have the authorized right to login to the system. | No change | 2 | 2 | Van Tuan, Thai | link
| User register | All user | User register |  | 2 | 1 | Van Tuan, Thai
| Change password | All user | Change password |  | 1 | 1 | Van Tuan, Thai
| Update user profile | Admin, Seller, Expert, Student, Customer | Update user profile |  | 1 | 1 | Van Tuan, Thai
| User authorization | Admin | User authorization |  | 1 | 1 | Van Tuan, Thai
Expert Feature | View all course | Expert | View all course | No change | 3 | 6 | Nguyen Duc, Le Duc,Viet Anh | link
| Add One Course |  | Add One Course |  | 3 | 3 | Nguyen Duc, Le Duc,Viet Anh
| Update One Course |  | Update One Course |  | 3 | 6 | Nguyen Duc, Le Duc,Viet Anh
| Delete One Course |  | Delete One Course |  | 10 | 7 | Nguyen Duc, Le Duc,Viet Anh
| View all Flashcard |  | View all Flashcard |  | 4 | 3 | Nguyen Duc, Le Duc,Viet Anh
| Add One Flashcard |  | Add One Flashcard |  | 5 | 4 | Nguyen Duc, Le Duc,Viet Anh
| Update One Flashcard |  | Update One Flashcard |  | 6 | 8 | Nguyen Duc, Le Duc,Viet Anh
| Delete One Flashcard |  | Delete One Flashcard |  | 7 | 7 | Viet Anh, Nguyen Huy
| View all Lesson |  | View all Lesson |  | 4 | 6 | Viet Anh, Nguyen Huy
| Add One Lesson |  | Add One Lesson |  | 5 | 6 | Nguyen Duc, Le Duc,Viet Anh
| Update One Lesson |  | Update One Lesson |  | 3 | 6 | Viet Anh, Nguyen Huy
| Delete One Lesson |  | Delete One Lesson |  | 4 | 5 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
Seller Feature | View Blog | Seller | Allow user to see all the products in the line of slider by clicking at the end of the line. | No change | 5 | 7 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy | link
| Create one Blog |  | Allow user to see all the blogs by clicking at the end of the line. |  | 4 | 6 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
| Update One Blog |  | User can view product's feeback which is in behind each product. |  | 7 | 5 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
| Delete One Blog | [5 empty] | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
Student Feature | Enroll | Student | Confirm joining one Course | No Change | 9 | 12 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy | link
| View Blog |  | Read Blog |  | 14 | 10 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
| View Course by Category |  | View Course organized by Category |  | 6 | 7 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
| View all Course |  | View all Course |  | 12 | 7 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
| View Enrolled Course |  | View Student's Enrolled Course |  | 5 | 8 | Nguyen Duc, Le Duc,Viet Anh, Van Tuan, Thai, Nguyen Huy
Admin Feature | Delete Account | Admin | Delete Account | No change | 4 | 3 | Viet Anh, Nguyen Huy | link
| Change Role Account |  | Change Role Account |  | 3 | 4 | Le Duc, Nguyen Huy