## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Functions/Screens
User Login Screen | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | 1 |  | Closed | TuanVu/Thai | 2023-02-14 | 2023-02-21 | Login/Register/Reset Password/Change Password/Change Profile
Write SRS for User Login screen | Write detailed functional specification for the User Login screen | 2 | https://docs.google.com/document/d/1v5td4U0EsaJ3piLhOymdewmD9t2gALcs/edit | Closed | TuanVu/Thai | 2023-02-14 | 2023-02-21
Write SDS for User Login screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the User Login screen | 3 | https://docs.google.com/document/d/1sfDGEE4ca6P4uvGp61RUYFS6-IXTN3wl/edit | Closed | TuanVu/Thai | 2023-02-14 | 2023-02-21
Write Code for User Login screen | Code & Unit test for the User Login screen | 4 | https://github.com/HyunNguyenn/SWR_Online_Learning | Open | TuanVu/Thai | 2023-02-14 | 2023-02-21
Integrate User Login screen with others | Integrate the User Login screen with other screens | 5 |  | Closed | TuanVu/Thai | 2023-02-14 | 2023-02-21 | User Authorization
Student Screen | This is a pop-up screen which allows the student to learning,view blog,course and enroll course | 6 |  | Closed | LeDuc/NgDuc/VietAnh/Huy | 2023-02-22 | 2023-02-28 | User Screen
Write SRS for Student screen | Write detailed functional specification for the User Login screen | 7 | https://docs.google.com/document/d/1v5td4U0EsaJ3piLhOymdewmD9t2gALcs/edit | Closed | LeDuc/NgDuc/VietAnh/Huy | 2023-02-22 | 2023-02-28
Write SDS for Student screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for Student screen | 8 | https://docs.google.com/document/d/1sfDGEE4ca6P4uvGp61RUYFS6-IXTN3wl/edit | Closed | LeDuc/NgDuc/VietAnh/Huy | 2023-02-22 | 2023-02-28
Write Code for Student screen | Code & Unit test for the Student screen | 9 | https://github.com/HyunNguyenn/SWR_Online_Learning | Open | LeDuc/NgDuc/VietAnh/Huy | 2023-02-22 | 2023-02-28
Integrate Student screen with others | Integrate the Student screen with other screens | 10 |  | Closed | LeDuc/NgDuc/VietAnh/Huy | 2023-02-22 | 2023-02-28
Admin Screen | This is a pop-up screen which allows the admin to manage account | 11 |  | Closed | TuanVu/Thai | 2023-03-01 | 2023-03-08 | Delete Account/Change Role Account
Write SRS for Admin screen | Write detailed functional specification for the Admin screen | 12 | https://docs.google.com/document/d/1v5td4U0EsaJ3piLhOymdewmD9t2gALcs/edit | Closed | TuanVu/Thai | 2023-03-01 | 2023-03-08
Write SDS for Admin screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for Admin screen | 13 | https://docs.google.com/document/d/1sfDGEE4ca6P4uvGp61RUYFS6-IXTN3wl/edit | Closed | TuanVu/Thai | 2023-03-01 | 2023-03-08
Write Code for Admin screen | Code & Unit test for the Admin screen | 14 | https://github.com/HyunNguyenn/SWR_Online_Learning | Closed | TuanVu/Thai | 2023-03-01 | 2023-03-08
Integrate Admin screen with others | Integrate the Admin with other screens | 15 |  | Closed | TuanVu/Thai | 2023-03-01 | 2023-03-08
Expert Screen | This is a pop-up screen which allows the expert to manage course and questions | 16 |  | Closed | LeDuc/NgDuc/VietAnh | 2023-03-09 | 2023-03-15 | CRUD Course-Lesson-Flashcard
Write SRS for Expert screen | Write detailed functional specification for the Expert screen | 17 | https://docs.google.com/document/d/1v5td4U0EsaJ3piLhOymdewmD9t2gALcs/edit | Closed | LeDuc/NgDuc/VietAnh | 2023-03-09 | 2023-03-15
Write SDS for Expert screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for Expert screen | 18 | https://docs.google.com/document/d/1sfDGEE4ca6P4uvGp61RUYFS6-IXTN3wl/edit | Closed | LeDuc/NgDuc/VietAnh | 2023-03-09 | 2023-03-15
Write Code for Expert screen | Code & Unit test for the Expert screen | 19 | https://github.com/HyunNguyenn/SWR_Online_Learning | Closed | LeDuc/NgDuc/VietAnh | 2023-03-09 | 2023-03-15
Integrate Expert screen with others | Integrate the Expert with other screens | 20 |  | Closed | VietAnh/Huy | 2023-03-09 | 2023-03-15
Seller Screen | This is a pop-up screen which allows the seller to manage blogs | 21 |  | Closed | VietAnh/Huy | 2023-03-09 | 2023-03-15 | CRUD Blog
Write SRS for Seller screen | Write detailed functional specification for the Seller screen | 22 | https://docs.google.com/document/d/1v5td4U0EsaJ3piLhOymdewmD9t2gALcs/edit | Closed | VietAnh/Huy | 2023-03-09 | 2023-03-15
Write SDS for Seller screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for Seller screen | 23 | https://docs.google.com/document/d/1sfDGEE4ca6P4uvGp61RUYFS6-IXTN3wl/edit | Closed | VietAnh/Huy | 2023-03-09 | 2023-03-15
Write Code for Seller screen | Code & Unit test for the Seller screen | 24 | https://github.com/HyunNguyenn/SWR_Online_Learning | Closed | VietAnh/Huy | 2023-03-09 | 2023-03-15
Integrate Seller screen with others | Integrate the Seller with other screens | 25 |  | Closed | VietAnh/Huy | 2023-03-09 | 2023-03-15