## Sheet1
ID | Task Name | Duration | Start | Finish | Resource Name
1 | Online Learning | 75 days | 2023-01-05 | 2023-03-21 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
2 | Software development | 70 days | 2023-01-06 | 2023-03-17 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
3 | Analyzing | 22 days | 2023-01-06 | 2023-01-27 | Vu Van Tuan ,Bui Viet Anh, Nguyen Duc Huy,
4 | Write SRS Document | 21 days | 2023-01-06 | 2023-01-27 | Nguyen Duc Huy, Le Hoang Thai , Bui Viet Anh
5 | Deliver Reports | 1 days | 2023-01-27 | 2023-01-28 | Vu Van Tuan ,Le Tuan Duc
6 | Designing | 12 days | 2023-01-13 | 2023-01-25 | Le Tuan Duc, Nguyen Tuan Duc
7 | Create Design Document | 5 days | 2023-01-19 | 2023-01-25 | Le Hoang Thai, Nguyen Duc Huy
8 | Update SRS Document | 3 days | 2023-01-21 | 2023-01-24 | Bui Viet Anh , Vu Van Tuan
9 | Create Testing Plan | 1 days | 2023-02-10 | 2023-02-11 | Le Tuan Duc, Nguyen Duc Huy
10 | Coding for: manage course, manage question | 7 days | 2023-02-11 | 2023-02-17 | Nguyen Tuan Duc , Bui Viet Anh
11 | Coding for: login, sign up, manager account system | 7 days | 2023-02-10 | 2023-02-16 | Vu Van Tuan , Bui Viet Anh, Le Tuan Duc
12 | Coding for: enroll courses, take lesson, take quiz | 7 days | 2023-02-18 | 2023-02-25 | Nguyen Duc Huy , Le Hoang Thai, Vu Van Tuan
13 | Coding for: manage expert, manage course price | 5 days | 2023-02-25 | 2023-03-02 | Nguyen Tuan Duc , Bui Viet Anh
14 | Coding for: blogs, manage blogs | 5 days | 2023-02-28 | 2023-03-05 | Vu Van Tuan , Bui Viet Anh, Le Tuan Duc
15 | Coding for: process enroll | 5 days | 2023-03-05 | 2023-03-10 | Nguyen Tuan Duc , Le Tuan Duc
16 | Coding for remain of all other | 4 days | 2023-03-10 | 2023-03-14 | Nguyen Tuan Duc , Bui Viet Anh
17 | Modified all system | 2 days | 2023-03-14 | 2023-03-16 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
18 | Full system testing | 5 days | 2023-03-13 | 2023-03-18 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
19 | Update test Document | 3 days | 2023-03-13 | 2023-03-16 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
20 | Execute Full ST& Fix bug | 2 days | 2023-03-16 | 2023-03-18 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
21 | Close | 9 days | 2023-03-15 | 2023-03-18 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
22 | Practice thesis presentation | 1 days | 2023-03-21 | 2023-03-22 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
23 | Finalize thesis presentation | 1 days | 2023-03-22 | 2023-03-23 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
24 | Final Document | 2 days | 2023-03-15 | 2023-03-17 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức
25 | Final presentation | 7 days | 2023-03-17 | 2023-03-24 | Thái,Tuấn,Huy,Đức,Vịệt Anh,Đức